## Sheet1
Date | Agenda | Action Item | Owner | Target Date | Status
11-Sep-26 | TTLI-1 Glue leakage issue | To be corrected | Gagan | 11-Sep | Pending
11-Sep-26 | Wide bottom issue in coated bars | To be Corrected and OPL to be prepared | Arvind Soni/k.k.pathak | 11-Sep | Pending
11-sep-26 | Book Weight Variation | Creme Hopper Level sensor centrelining | Lalit/Ashish | 11-Sep | Pending
11-sep-26 | Test | Test | Test | 12-Sep | Pending
12-Sep | Particles found on Creme sieve hopper | QA team to involved and checked | Shikha | 12-Sep | Pending
12-Sep | HLL Cooling tunnel condensate water leakage issue | To be checked | Ravinder | 12-Sep | Pending
| Laser vaccum filter chocking | Laser vacuum filter chocking issue to escalate to OEM for solution | Deepesh Verma